## Overview
Course | Designing Playful Experience
Members & Roles | Lejie Lin Development and level design
Shangshu Shi Sound Design and level design
Yu Zhou Game Director and level design
Product name | Duckrossing
type | Hypercasual/Puzzle/Walking Sim
USP(unique selling point) | Alternative Controller
Links | https://yuzhou1655.github.io/Duckrossing/

## TODO List
Feature | State | Hour cost | Priority | Assign to | Note
Game Design Document | Wip | >2 | Not in Rush | YZ
1 Level Design | Done | <1 | Important | ALL | meeting 11/19 3:30pm
Transition from level 1 to level 2 | Done | 2 | Important | YZ
art assessts for 3 levels | PlanChange | >2 | Important | YZ
Start prototyping with actors | Done | >2 | Important | LLJ
Developmen of Level 2 | Done | 2 | Important | LLJ
Learn the code, finalize Design on 1 level | Done | 2 | Important | MNT
Development of Level 4 | Done | 2 | Important | MNT
Development of Level 3 | PlanChange |  | Important
Adittional Control (move vertical/move backwards) | Done | >2 | Important | YZ
progress report meeting and discussion on feedback | Done | <1 | Important | ALL | meeting 11/21 21:30
Redesign Ending Logic | Done | 2 | Not in Rush | ALL
Redesign and Develop intro | Done | >2 | Important | YZ
Development of SpeedUp and Fly | Done | >2 | Important | YZ
Add Player Guidance | Done | 1 | Important | YZ
Better Level Transition | Done | 2 | Important | YZ
Redesign Duck related UI | Done | 2 | Important | YZ
Replace AI generated Images | PlanChange | 2 | Important
Redo Death Animation | Done | 1 | Important | YZ
Redevelopment Level 4 （now lvl5 | Done | 1 | Important | MNT YZ
ReDesign new level 4 | Done | <1 | Important | YZ
Art Assessts for new level 4 | Done | 1 | Important | YZ
Art assessts for level 4 （now lvl5 | Done | 1 | Important | YZ
Redesign Level 5（now lvl6 | Done | 2 | Important | ALL
Art assessts for level 5 （now lvl6 | Done | 2 | Important | YZ
Redo TRIPPED, SLIPPED | Done | 1 | Important | LLJ YZ
Development of Level 5 （now lvl6 | Done | >2 | Important | YZ
Sound Design of Level 5 （now lvl6 | Done | 1 | Important | MNT
Design Ending | Done | <1 | Important | YZ
Developmen Ending | Done | 1 | Important | YZ
Sound Design of Ending | Done | <1 | Important | YZ
Redo Ending | Done | 2 |  | YZ
Bug Fix | Done | >2 | Important | ALL
BTS Trailor Viedo | Done | >2 | - | LLJ
Promotion Video | Done | 2 | Not in Rush | ALL

## Bug List
Feature | State | Hour cost | Priority | Assign to | Note
Feet Size level1 2 | Done | - | Not in Rush
Feet Position level 1 2 | Done | <1 | Not in Rush
Button Not Working Correctly | Done | 2 | Important
WingImage can`t change | Wip |  | Wait Until..
Runing Movement | Done
Death reset ... | Wip | >2 | Important
Gator AI | Done | 1
Season Ending White Fade | PlanChange
Level 5 Ending | Done
Level 2 Stretch Distance | Done
Level 2 Ending | Done

## PlayTestFeedBack
Feature | State | Hour cost | Priority | Assign to | Note
Early Stretch | Done | 1 | Important
lvl 1 too hard | Done | 1 | Important
CTRL feet cable | Done | 1 | Important
lvl5 Bat Visble | Wip | <1
lvl6 Winter Frozen slower | Done | <1
lvl6 Spring Gator Speed Up | Done | <1

## Milestones
2023-11-21 | 2023-11-30 | 2023-12-05
All actor tested | Level Done | Basically Everything Done
Art assessts Done | Audio Done
Level Desin Done | Start working on Heaven level
Additional Control Scratch | Additional Control Done | 2023-12-07
Bug Fixed
Promotion Video Done
Game Design Document Done
Submitted to ALT CTRL
Cooperation methods & analysis
Chat: Wechat Voice&Video&Screen Share: in person File: Google Drive